## OPTIONS
OPTIONS | OPTION 1 New Virtual Host | OPTION 2 New Single Arm Load Balancer | OPTION 3 New Load Balancer
Description (Option Outline) | Create new virtual host for CJIM UFS | Create a "Single arm" load balancer on F5 to point to Apache | Create new LB that will terminate SSL and go to directly to weblogic servers with new certs (remove Apache from this option)
PROS | 1. Dedicated virtual host that will not impact other apps 2. Can be deployed in QC and PROD independent of other apps 3. Proven solution with NNS 2.1 new virtual host created for NNS being decoupled 4. Minor change to the workflow - the solution is the same | 1. Would mimic current set up in PROD 2. Minor change to the workflow | 1. Not dependent on Apache and virtual hosts 2. Streamlined solution
CONS | 1. Dependent on Common Services (Apache) resource for set up who does not have the cycles at this time to create a new Virtual Host 2. No value added by going through a virual host | 1. Dependent on AWIS resource for set up who does not have the cycles at this time to create a new Virtual Host 2. No value added by going through a virual host | 1. Workflow changes - architectural change 2. Does Architect and Innovation need to approve this solution? 3. Is DSB approval required?
Risks/Dependencies | 1. Dependent on the availabilty of Apache resource | 1. Dependent on the availabilty of AWIS resource 2. Dependent on Network availability | 1. CJIM may need to change their code? 2. Can the Load Balancer create the same match expression that comes from Apache? 3. Can the Load Balancer distribute across nodes?
Timeline | Unknown |  | Network: 1 Day
Effort/Cost | 1. Common Services (Apache) effort = ? 2. Network Group (Load Balancer) effort = ? 3. VPN (New ACLs) effort = ? 4. AWIS (Weblogic) = ? 5. CJIM DEV = ? | 1. Common Services (Apache) effort = ? 2. Network Group (Load Balancer) effort = ? 3. VPN (New ACLs) effort = ? 4. AWIS (Weblogic) = ? 5. CJIM DEV = ? | 1. Network Group (Load Balancer) effort = 1 Day 2. VPN (New ACLs) effort = ? 3. AWIS (Weblogic) = ? 4. CJIM DEV = ?
Recommendation

## MISC
Ed Daigle | Common Services (Apache)
Loc Tran | Common Services (Apache) - Ed's backup
Derek Reynolds | AWIS (Weblogic)
Oleg Maier | Network (Load Balancer)
Mahmoud Mattar | VPN